## Slide 1: Twitter Clone Sprint 1 Review
Mon, Mar 20, 2023

## Slide 2: Sprint 1 Review
Sprint 1 Accomplishments
Backend setup with Rails
Frontend frameworks setup with React and ESBuild
Devise setup (basic)
Basic Frontend UI setup, including Sidebar, Suggestions, Feed, Profile, and Login UI.
Sprint 2 Goals
Implkement Notifications, Messages, and Sign-In/Up UI’s.
Finalize User model and integrate with registration / authentication
Implement full Tweet functionality
Chart: Estimated Hours
| Hours
Frontend | 17
Backend | 5
22
Sprint 2 Risks
Backend Integration may pose risks due to version discrepancies. Extra time has been added to account for this.

## Slide 3: Sprint 2 Actions
Action | Sub-Action | Estimated Hours | Category | Due Date | Status
Frontend UI | Implement Notifications section | 2 | Frontend | 3/21/2023 | Not Started
Frontend UI | Implement Messages section | 3 | Frontend | 3/23/2023 | Not Started
Tweet UI | Create tweet UI | 4 | Frontend | 3/20/2023 | Future
Tweet Management | Implement tweet CRUD functionality | 1 | Backend | 3/22/2023 | Not Started
User Authentication | Finalize User model | 1 | Backend | 3/22/2023 | Not Started
Tweet Management | Create tweet model | 0.5 | Backend | 3/23/2023 | Not Started
User Authentication | Implement Sign in/up UI | 4 | Frontend | 3/23/2023 | Not Started
User Authentication | Integrate user profile with backend | 2 | Full Stack | 3/24/2023 | Not Started
Tweet Management | Integrate New Tweet UI with Backend | 4 | Frontend | 3/25/2023 | Not Started