## Slide 1: Twitter Clone Pre-Review
Fri, Mar 10, 2023

## Slide 2: Project Overview
The Twitter Clone project aims to create a social media platform with tweet, follow, and hashtag search functionality, as well as real-time updates and like functionality.
Chart: 
| Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6
Start Date | 44998 | 45005 | 45012 | 45019 | 45026 | 45033
Length | 7 | 7 | 7 | 7 | 7 | 7
Milestone Description | Due Date
Completion of Sprint 1 | Mar 17
Completion of Sprint 2 | Mar 24
Completion of Sprint 3 | Mar 31
Completion of Sprint 4 | Apr 7
Completion of Sprint 5 | Apr 14
Completion of Sprint 6 | Apr 21
Completion of final testing and bug fixing | Apr 28
Project launch and deployment | May 5
Team Member | Role | High-Level Responsibilities
ChatGPT (Project Manager) | Project Manager | Overall project management, task delegation, stakeholder communication, timeline management, risk assessment and mitigation
Matt Burns | Full Stack Developer | Frontend and backend development, database design and management, code testing and debugging, feature implementation, adherence to project timelines and milestones

## Slide 3: Project Risks
Risk | Risk Description | Risk Level | Mitigation
Technical risks | Potential technical issues or difficulties in implementing required features. | Medium | Conduct thorough research and planning, collaborate with technical experts, conduct frequent testing to identify and resolve technical issues early in the development process.
Schedule risks | Potential delays or challenges that may impact the project schedule. | High | Implement a flexible schedule with built-in contingencies, regularly review progress against the project plan, communicate any potential delays or challenges to stakeholders as soon as possible.
Resource risks | Potential resource constraints such as lack of personnel, equipment, or funding. | Medium | Conduct regular resource assessments, communicate resource needs to stakeholders, explore alternative resources if needed, prioritize critical tasks to ensure that available resources are used effectively.
Security risks | Potential vulnerabilities to security breaches or attacks. | High | Follow established security best practices, use secure authentication methods, implement encryption, conduct regular security audits, use reputable third-party libraries or services as needed.
User adoption risks | Potential failure to gain significant user adoption due to competition or lack of interest. | Low | Conduct market research to identify user needs and preferences, implement user-friendly features, conduct user testing to identify and address usability issues, engage in marketing and outreach activities to increase visibility and interest in the platform.

## Slide 4: Frontend Work
Build a user interface that is intuitive, user-friendly, and visually appealing
Primary frontend language: TypeScript with React, with HTML, CSS, and JavaScript as supporting languages
Divided into six sprints, with each sprint focusing on specific features and functionality
First sprint: Setting up project structure, creating login and registration pages, and implementing basic homepage layout
Subsequent sprints: Implementing tweet and follow functionality, real-time updates, hashtag search, and like functionality
Work closely with backend team to ensure proper integration and data fetching/display
Code testing and debugging to ensure seamless, error-free user experience.

## Slide 5: Backend Work
Building a Ruby on Rails backend that is robust, scalable, and secure
Primary backend language used will be Ruby, with Rails as the supporting framework
Divided into six sprints, each focusing on specific features and functionality
First sprint will focus on setting up the project structure, creating the initial database schema, and implementing the basic user authentication system
Subsequent sprints will focus on implementing additional functionality such as tweet and follow functionality, real-time updates, hashtag search, and like functionality
Backend team will work closely with the frontend team to ensure proper integration and data storage
Code testing and debugging will be an important part of the backend development process

## Slide 6: Project Resources
Chart: 
| 1 | 2 | 3 | 4 | 5 | 6
Backend | 24 | 22 | 14 | 12 | 10 | 8
Frontend | 24 | 22 | 14 | 12 | 10 | 8
48
44
28
24
20
16

## Slide 7: First Sprint Tasks
Category | Action | Sub-Action | Estimated Hours
Frontend | Frontend Setup | Install Node.js and React | 2
 |  | Setup React project with ESBuild | 2
 | Frontend UI | Create basic UI layout | 4
Backend | Backend Setup | Install Ruby and Rails | 2
 |  | Setup Rails project with ESBuild | 2
 | User Authentication | Setup Devise | 4
Total |  |  | 16

## Slide 8: Q&A

## Slide 9: Appendix

## Slide 10: Key Deliverables
Milestone | Due Date | Key Deliverables
Completion of Sprint 1: Project Setup and User Authentication | Mar 17 | Frontend setup with Node.js and React, Backend setup with Ruby and Rails, User authentication functionality with Devise, Basic UI layout
Completion of Sprint 2: Tweet Management and User Interface | Mar 24 | Tweet model creation, CRUD functionality for tweets, User interface for creating and viewing tweets, Integration of Devise for user authentication
Completion of Sprint 3: Follow Management and Controller Actions | Mar 31 | Follow model creation, Follow/unfollow functionality, User interface for following/unfollowing users, Controller actions for tweets and follows
Completion of Sprint 4: Real-Time Updates and Hashtag Search | Apr 7 | Setup of ActionCable for real-time updates, Real-time updates for tweets, Hashtag model creation, Hashtag search functionality, User interface for searching hashtags
Completion of Sprint 5: Tweet Likes and Code Refactoring | Apr 14 | Like model creation, Tweet liking functionality, Code refactoring for readability and maintainability
Completion of Sprint 6: Testing and Bug Fixing | Apr 21 | Creation and execution of test cases, Resolution of any issues found during testing, Final testing and bug fixing
Completion of final testing and bug fixing | Apr 28 | Final review of code and functionality, Resolution of any final issues or bugs
Project launch and deployment | May 5 | Deployment of Twitter Clone to production environment, Final user acceptance testing and sign-off

## Slide 11: Frontend Actions
Sprint | Action | Estimated Hours
1 | Project structure setup | 6
1 | Login and registration pages | 8
1 | Homepage layout implementation | 10
2 | Tweet functionality implementation | 12
2 | Follow functionality implementation | 10
3 | Real-time updates implementation | 14
4 | Hashtag search implementation | 12
5 | Like functionality implementation | 10
6 | UI/UX testing and debugging | 8

## Slide 12: Backend Actions
Sprint | Action | Estimated Hours
1 | Project structure setup | 6
1 | Database schema creation | 8
1 | User authentication implementation | 10
2 | Tweet functionality implementation | 12
2 | Follow functionality implementation | 10
3 | Real-time updates implementation | 14
4 | Hashtag search implementation | 12
5 | Like functionality implementation | 10
6 | Code testing and debugging | 8